## NAC Plan Matrix
WBS ID | Name | Type | Parent | Owner Role | Effort (PD) | Duration (days) | Planned Start | Planned Finish | Predecessors | Resources (skills) | Assumptions | Notes
E01 | NAC Program Foundations & Governance | Epic |  | Security Architecture | 20 | 10 | 2026-04-01 | 2026-04-11 |  | Security Architecture | Avg 2 FTE; dates are draft and subject to CAB.
E02 | Forescout Platform Enablement & RADIUS for Wired MAB | Epic |  | Security Operations | 35 | 18 | 2026-04-15 | 2026-05-03 | E01 | Security Operations | Avg 2 FTE; dates are draft and subject to CAB.
E03 | Access Switch AAA & Edge Hardening (MAB + Multi-Auth + L2 Protections) | Epic |  | Network Engineering | 45 | 23 | 2026-04-15 | 2026-05-08 | E01,E02 | Network Engineering | Avg 2 FTE; dates are draft and subject to CAB.
E04 | Core L3 Enforcement (Minimum Viable Remediation ACLs) | Epic |  | Network Engineering | 30 | 15 | 2026-05-06 | 2026-05-21 | E01,E02 | Network Engineering | Avg 2 FTE; dates are draft and subject to CAB.
E05 | Posture Integrations (Forescout, CrowdStrike, Tanium, Qualys, Intune/Jamf) | Epic |  | Security Operations | 50 | 25 | 2026-05-06 | 2026-05-31 | E02 | Security Operations | Avg 2 FTE; dates are draft and subject to CAB.
E06 | Wireless Integration & Core Enforcement | Epic |  | Network Engineering | 16 | 8 | 2026-05-20 | 2026-05-28 | E04 | Network Engineering | Avg 2 FTE; dates are draft and subject to CAB.
E07 | Observability, Accounting, SIEM & ITSM | Epic |  | Security Operations | 24 | 12 | 2026-05-20 | 2026-06-01 | E02,E04,E05 | Security Operations | Avg 2 FTE; dates are draft and subject to CAB.
E09 | Runbooks, Training & Break‑Glass | Epic |  | Service Desk | 16 | 8 | 2026-05-20 | 2026-05-28 | E02,E03,E04,E05,E07 | Service Desk | Avg 2 FTE; dates are draft and subject to CAB.
E08 | Pilot, Rollout & Change Management | Epic |  | Program Management | 36 | 18 | 2026-06-03 | 2026-06-21 | E01,E02,E03,E04,E05,E06,E07,E09 | Program Management | Avg 2 FTE; dates are draft and subject to CAB.
E10 | IoT/OT Device Inventory, Governance & Lifecycle (Adds/Moves/Changes) | Epic |  | Security Architecture | 40 | 20 | 2026-04-22 | 2026-05-12 | E01 | Security Architecture | Avg 2 FTE; dates are draft and subject to CAB.
S01-01 | Publish NAC Program Charter & RACI | Story | E01 | Security Architecture | 6 | 3 | 2026-04-01 | 2026-04-04 | E01 | Security Architecture | Avg 2 FTE; story schedule aligns within epic window.
S01-02 | Golden Templates & Naming Standards | Story | E01 | Network Engineering | 7 | 4 | 2026-04-01 | 2026-04-05 | S01-01 | Network Engineering | Avg 2 FTE; story schedule aligns within epic window.
S01-03 | Success Metrics & Risk Register | Story | E01 | Program Management | 5 | 3 | 2026-04-01 | 2026-04-04 | S01-01 | Program Management | Avg 2 FTE; story schedule aligns within epic window.
S02-01 | Deploy Forescout RADIUS & CoA (Lab) | Story | E02 | Security Operations | 6 | 3 | 2026-04-15 | 2026-04-18 | E02 | Security Operations | Avg 2 FTE; story schedule aligns within epic window.
S02-02 | RADIUS HA & Health Monitoring | Story | E02 | Security Operations | 6 | 3 | 2026-04-15 | 2026-04-18 | S02-01 | Security Operations | Avg 2 FTE; story schedule aligns within epic window.
S02-03 | Pilot Switch Integration | Story | E02 | Network Engineering | 8 | 4 | 2026-04-15 | 2026-04-19 | S02-01 | Network Engineering | Avg 2 FTE; story schedule aligns within epic window.
S02-04 | SNMP Discovery & Guardrails | Story | E02 | Network Engineering | 5 | 3 | 2026-04-15 | 2026-04-18 | E02 | Network Engineering | Avg 2 FTE; story schedule aligns within epic window.
S03-01 | AAA Split on Access Switches | Story | E03 | Network Engineering | 10 | 5 | 2026-04-15 | 2026-04-20 | E03 | Network Engineering | Avg 2 FTE; story schedule aligns within epic window.
S03-02 | Interface Profiles: MAB + Multi‑Auth | Story | E03 | Network Engineering | 12 | 6 | 2026-04-15 | 2026-04-21 | S03-01 | Network Engineering | Avg 2 FTE; story schedule aligns within epic window.
S03-03 | Edge L2 Protections | Story | E03 | Network Engineering | 12 | 6 | 2026-04-15 | 2026-04-21 | S03-01 | Network Engineering | Avg 2 FTE; story schedule aligns within epic window.
S03-04 | MAC‑Move & Anomaly Monitoring | Story | E03 | Security Operations | 6 | 3 | 2026-04-15 | 2026-04-18 | S03-01 | Security Operations | Avg 2 FTE; story schedule aligns within epic window.
S04-01 | Define ACL‑MVS Objects | Story | E04 | Security Operations | 10 | 5 | 2026-05-06 | 2026-05-11 | E04 | Security Operations | Avg 2 FTE; story schedule aligns within epic window.
S04-02 | Attach ACL‑MVS on Pilot VLANs | Story | E04 | Network Engineering | 12 | 6 | 2026-05-06 | 2026-05-12 | S04-01 | Network Engineering | Avg 2 FTE; story schedule aligns within epic window.
S04-03 | Logging & Drift Controls | Story | E04 | Security Operations | 8 | 4 | 2026-05-06 | 2026-05-10 | S04-02 | Security Operations | Avg 2 FTE; story schedule aligns within epic window.
S05-01 | SecureConnector Gate | Story | E05 | Security Operations | 10 | 5 | 2026-05-06 | 2026-05-11 | E05 | Security Operations | Avg 2 FTE; story schedule aligns within epic window.
S05-02 | CrowdStrike Sensor Health Gate | Story | E05 | Security Operations | 10 | 5 | 2026-05-06 | 2026-05-11 | E05 | Security Operations | Avg 2 FTE; story schedule aligns within epic window.
S05-03 | Tanium Online Baseline Gate | Story | E05 | Security Operations | 10 | 5 | 2026-05-06 | 2026-05-11 | E05 | Security Operations | Avg 2 FTE; story schedule aligns within epic window.
S05-04 | Qualys Agent Reporting Gate | Story | E05 | Security Operations | 10 | 5 | 2026-05-06 | 2026-05-11 | E05 | Security Operations | Avg 2 FTE; story schedule aligns within epic window.
S05-05 | Intune/Jamf Enrollment Gate | Story | E05 | Endpoint Engineering | 10 | 5 | 2026-05-06 | 2026-05-11 | E05 | Endpoint Engineering | Avg 2 FTE; story schedule aligns within epic window.
S06-01 | WLAN Session Correlation in Forescout | Story | E06 | Security Operations | 8 | 4 | 2026-05-20 | 2026-05-24 | E06 | Security Operations | Avg 2 FTE; story schedule aligns within epic window.
S06-02 | Core L3 ACL Alignment for WLAN | Story | E06 | Network Engineering | 8 | 4 | 2026-05-20 | 2026-05-24 | E04 | Network Engineering | Avg 2 FTE; story schedule aligns within epic window.
S07-01 | RADIUS Accounting to SIEM | Story | E07 | SIEM/Analytics | 8 | 4 | 2026-05-20 | 2026-05-24 | E02 | SIEM/Analytics | Avg 2 FTE; story schedule aligns within epic window.
S07-02 | Posture Event Integration | Story | E07 | Security Operations | 8 | 4 | 2026-05-20 | 2026-05-24 | E05 | Security Operations | Avg 2 FTE; story schedule aligns within epic window.
S07-03 | ITSM Ticket Automation | Story | E07 | Service Desk | 8 | 4 | 2026-05-20 | 2026-05-24 | E05 | Service Desk | Avg 2 FTE; story schedule aligns within epic window.
S08-01 | Lab Validation & Test Plan | Story | E08 | Program Management | 12 | 6 | 2026-06-03 | 2026-06-09 | E02,E03,E04,E05 | Program Management | Avg 2 FTE; story schedule aligns within epic window.
S08-02 | Pilot Site Rollout | Story | E08 | Program Management | 12 | 6 | 2026-06-03 | 2026-06-09 | S08-01,E06,E07,E09 | Program Management | Avg 2 FTE; story schedule aligns within epic window.
S08-03 | Phased Expansion | Story | E08 | Program Management | 12 | 6 | 2026-06-03 | 2026-06-09 | S08-02 | Program Management | Avg 2 FTE; story schedule aligns within epic window.
S09-01 | Ops Runbooks & Break‑Glass | Story | E09 | Service Desk | 8 | 4 | 2026-05-20 | 2026-05-24 | E02,E03,E04,E05,E07 | Service Desk | Avg 2 FTE; story schedule aligns within epic window.
S09-02 | Training & Knowledge Transfer | Story | E09 | Service Desk | 8 | 4 | 2026-05-20 | 2026-05-24 | S09-01 | Service Desk | Avg 2 FTE; story schedule aligns within epic window.
S10-01 | IoT/OT Governance Policy | Story | E10 | Security Architecture | 6 | 3 | 2026-04-22 | 2026-04-25 | E10 | Security Architecture | Avg 2 FTE; story schedule aligns within epic window.
S10-02 | Passive Discovery Enablement | Story | E10 | OT Engineering | 6 | 3 | 2026-04-22 | 2026-04-25 | E10 | OT Engineering | Avg 2 FTE; story schedule aligns within epic window.
S10-03 | Canonical Inventory Schema | Story | E10 | Security Architecture | 6 | 3 | 2026-04-22 | 2026-04-25 | E10 | Security Architecture | Avg 2 FTE; story schedule aligns within epic window.
S10-04 | Switch/DHCP Telemetry Integration | Story | E10 | Network Engineering | 6 | 3 | 2026-04-22 | 2026-04-25 | E10 | Network Engineering | Avg 2 FTE; story schedule aligns within epic window.
S10-05 | Identification & Validation Workflow | Story | E10 | Security Operations | 6 | 3 | 2026-04-22 | 2026-04-25 | S10-02,S10-03,S10-04 | Security Operations | Avg 2 FTE; story schedule aligns within epic window.
S10-06 | AMC (Add/Move/Change) Process | Story | E10 | Change Management | 5 | 3 | 2026-04-22 | 2026-04-25 | S10-01,S10-03 | Change Management | Avg 2 FTE; story schedule aligns within epic window.
S10-07 | Onboarding Checklist for New IoT/OT Devices | Story | E10 | OT Engineering | 5 | 3 | 2026-04-22 | 2026-04-25 | S10-01 | OT Engineering | Avg 2 FTE; story schedule aligns within epic window.
S10-08 | Exception & Legacy Handling | Story | E10 | Security Architecture | 5 | 3 | 2026-04-22 | 2026-04-25 | S10-01 | Security Architecture | Avg 2 FTE; story schedule aligns within epic window.
S10-09 | Dashboards & Reporting | Story | E10 | Security Operations | 5 | 3 | 2026-04-22 | 2026-04-25 | S10-02,S10-05 | Security Operations | Avg 2 FTE; story schedule aligns within epic window.
S10-10 | Retirement & Incident Runbook | Story | E10 | Security Operations | 6 | 3 | 2026-04-22 | 2026-04-25 | S10-05 | Security Operations | Avg 2 FTE; story schedule aligns within epic window.

## Role Load (PD)
Epic | Role | Effort (PD)
E01 | Network Engineering | 7
E01 | Program Management | 5
E01 | Security Architecture | 6
E02 | Network Engineering | 13
E02 | Security Operations | 12
E03 | Network Engineering | 34
E03 | Security Operations | 6
E04 | Network Engineering | 12
E04 | Security Operations | 18
E05 | Endpoint Engineering | 10
E05 | Security Operations | 40
E06 | Network Engineering | 8
E06 | Security Operations | 8
E07 | SIEM/Analytics | 8
E07 | Security Operations | 8
E07 | Service Desk | 8
E08 | Program Management | 36
E09 | Service Desk | 16
E10 | Change Management | 5
E10 | Network Engineering | 6
E10 | OT Engineering | 11
E10 | Security Architecture | 17
E10 | Security Operations | 17

## Epic Summary
Epic | Name | Epic Effort (PD) | Duration (days) | Planned Start | Planned Finish | Stories Effort (PD)
E01 | NAC Program Foundations & Governance | 20 | 10 | 2026-04-01 | 2026-04-11 | 18
E02 | Forescout Platform Enablement & RADIUS for Wired MAB | 35 | 18 | 2026-04-15 | 2026-05-03 | 25
E03 | Access Switch AAA & Edge Hardening (MAB + Multi-Auth + L2 Protections) | 45 | 23 | 2026-04-15 | 2026-05-08 | 40
E04 | Core L3 Enforcement (Minimum Viable Remediation ACLs) | 30 | 15 | 2026-05-06 | 2026-05-21 | 30
E05 | Posture Integrations (Forescout, CrowdStrike, Tanium, Qualys, Intune/Jamf) | 50 | 25 | 2026-05-06 | 2026-05-31 | 50
E06 | Wireless Integration & Core Enforcement | 16 | 8 | 2026-05-20 | 2026-05-28 | 16
E07 | Observability, Accounting, SIEM & ITSM | 24 | 12 | 2026-05-20 | 2026-06-01 | 24
E09 | Runbooks, Training & Break‑Glass | 16 | 8 | 2026-05-20 | 2026-05-28 | 16
E08 | Pilot, Rollout & Change Management | 36 | 18 | 2026-06-03 | 2026-06-21 | 36
E10 | IoT/OT Device Inventory, Governance & Lifecycle (Adds/Moves/Changes) | 40 | 20 | 2026-04-22 | 2026-05-12 | 56