## Project Tracker
Phase | Timeline | Objective | KPI | Owner | Status
Phase 1: Visibility & Staffing | Weeks 1–4 | Validate all CVS subnets and network devices in Forescout | 100% of production switches and wireless controllers validated in Forescout |  | Not Started
Phase 1: Visibility & Staffing | Weeks 1–4 | Hire or augment staff with a Forescout-certified engineer | FSCA certification completed |  | Not Started
Phase 1: Visibility & Staffing | Weeks 1–4 | Train internal resource (Aaron) via FSCA | Forescout admin onboarded or augmentation contract signed |  | Not Started
Phase 2: Policy Definition & Enforcement | Weeks 5–8 | Define compliance policies for all device types | Compliance policies defined and documented for 100% of device categories |  | Not Started
Phase 2: Policy Definition & Enforcement | Weeks 5–8 | Implement posture checks for Windows, MacOS, printers, cameras, and IoT | 90% of managed devices pass compliance checks |  | Not Started
Phase 2: Policy Definition & Enforcement | Weeks 5–8 | Establish onboarding workflows for unknown devices | Onboarding workflow published and adopted by device owners |  | Not Started
Phase 3: Integration Enablement | Weeks 9–12 | Integrate Forescout with CrowdStrike, Intune/JAMF, Qualys, ServiceNow, Splunk, and Palo Alto | 6 integrations live and operational |  | Not Started
Phase 3: Integration Enablement | Weeks 9–12 | Automate enforcement actions based on posture and threat data | 95% of CrowdStrike-managed devices validated in Forescout |  | Not Started
Phase 4: Continuous Improvement & Reporting | Weeks 13–16 | Monitor compliance drift and posture changes | Weekly compliance reports generated in Splunk |  | Not Started
Phase 4: Continuous Improvement & Reporting | Weeks 13–16 | Generate dashboards and reports for audit readiness | 100% of policy violations logged and alerted |  | Not Started
Phase 4: Continuous Improvement & Reporting | Weeks 13–16 | Tune policies based on behavioral insights | 90% reduction in rogue device dwell time |  | Not Started